PAIS — Personal Agency Immune System

Project Implementation Plan  ·  Agent Methodology  ·  Milestones

0  EMPIRICAL BASELINE — What the Verifiable Run Proved

The live test run (Round 3 falsifiability instrument) produced the following ground truth before any implementation begins:

| Test | Result | ARS | Finding |
| --- | --- | --- | --- |
| T1 Atrophy Detection | ❌ FAIL | 0.543 < 0.70 | ARS formula under-scores atrophy; classification correct |
| T2 Scaffolding Non-Interv. | ✅ PASS | 0.066 | Asymmetric error principle holds; ND users protected |
| T3 Circuit Breaker | ❌ FAIL | 0.575 | CB never fires because ARS never reaches threshold |
| T4 Hard Floor Irreversible | ✅ PASS | N/A | Platform floor solid; not user-overridable |
| T5 Cold Start | ✅ PASS | 0.0 | Insufficient history → no intervention |
| T6 Expert Non-Interv. | ✅ PASS | N/A | Expert suppression works; conf 0.83 |
| Monte Carlo F1 | ❌ FAIL | F1 = 0.0 | ARS threshold too high; 0/200 atrophy trials triggered |

→ Root cause identified: ARS threshold (0.70) is miscalibrated relative to formula output range. Fix is one parameter change. Architecture is sound.

1  AGENT METHODOLOGY

Five specialist agents operate in sequence with defined handoff contracts. No agent proceeds without the prior agent's exit artifact.

Agent A1 — CALIBRATION AGENT

Purpose: Recalibrate ARS formula weights and threshold via grid search on synthetic data.

Responsibilities & Exit Criteria:

Input: current pais_core.py + test harness

Method: grid search over verbatim_rate weight [0.30–0.55], threshold [0.40–0.70]

Output: calibrated_params.json with optimal weights + threshold

Exit criterion: atrophy_f1 ≥ 0.80 AND scaffolding_fp ≤ 0.10 on 1,000-trial Monte Carlo

Agent A2 — DIFFERENTIAL DIAGNOSIS AGENT

Purpose: Stress-test the five-factor fingerprint against edge cases: neurodivergent + high-stakes, expert + novel domain, cold-start with partial history.

Responsibilities & Exit Criteria:

Input: calibrated_params.json + pais_core.py

Method: adversarial synthetic profiles (12 edge case archetypes)

Output: edge_case_report.json + updated classify_delegation_pattern()

Exit criterion: 0 false positives on neurodivergent archetypes; < 15% uncertain rate

Agent A3 — INTEGRATION AGENT

Purpose: Wire pais_core.py into API middleware layer. Build friction injection interface. Implement circuit breaker with 72h expiry.

Responsibilities & Exit Criteria:

Input: calibrated pais_core.py + edge_case_report.json

Method: FastAPI middleware wrapper; Redis for session state; circuit breaker state machine

Output: pais_middleware.py + docker-compose.yml

Exit criterion: end-to-end latency < 50ms p95; all unit tests pass in container

Agent A4 — GOVERNANCE AGENT

Purpose: Implement user-sovereignty controls: settings UI, 30-day expiry, audit log, third-party auditor interface.

Responsibilities & Exit Criteria:

Input: pais_middleware.py

Method: REST endpoints for user override, platform floor config, audit trail

Output: governance_api.py + audit_schema.sql

Exit criterion: user can override any non-PLATFORM_FLOOR decision in ≤ 2 clicks; audit log immutable

Agent A5 — VALIDATION AGENT

Purpose: Run full falsifiability suite against integrated system. Produce go/no-go recommendation.

Responsibilities & Exit Criteria:

Input: full integrated stack

Method: 5,000-trial Monte Carlo; 12 edge case archetypes; latency benchmarks

Output: validation_report.pdf with PAIS_VIABLE: true/false

Exit criterion: PAIS_VIABLE = true OR documented kill condition with root cause

2  PROJECT TODO LIST

PHASE 0 — IMMEDIATE FIX (Day 1, 2–4 hours)

| ID | Agent | Task | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| P0-01 | A1 | Lower ARS_INTERVENTION_THRESHOLD from 0.70 → 0.45 in pais_core.py | CRITICAL | 30 min |
| P0-02 | A1 | Reweight ARS formula: verbatim_rate 0.30→0.45, cross_domain 0.15→0.10 | CRITICAL | 30 min |
| P0-03 | A1 | Re-run test suite; confirm T1 and T3 now pass | CRITICAL | 15 min |
| P0-04 | A1 | Run 1,000-trial Monte Carlo; confirm F1 ≥ 0.80 and scaffolding_fp ≤ 0.10 | CRITICAL | 1 hr |
| P0-05 | A1 | Commit calibrated_params.json with winning weights | HIGH | 15 min |

PHASE 1 — DIFFERENTIAL DIAGNOSIS HARDENING (Days 2–3)

| ID | Agent | Task | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| P1-01 | A2 | Define 12 adversarial user archetypes (ADHD+high-stakes, expert+novel domain, etc.) | HIGH | 2 hrs |
| P1-02 | A2 | Generate synthetic interaction histories for each archetype | HIGH | 3 hrs |
| P1-03 | A2 | Run classify_delegation_pattern() against all 12; log misclassifications | HIGH | 1 hr |
| P1-04 | A2 | Tune declared_neurodivergent prior weight (currently +0.30); validate no ND false positives | HIGH | 2 hrs |
| P1-05 | A2 | Add domain_novelty_score factor to fingerprint (new domain = not atrophy) | MEDIUM | 3 hrs |
| P1-06 | A2 | Update test suite with 12 archetype test cases; all must pass | HIGH | 2 hrs |

PHASE 2 — MIDDLEWARE INTEGRATION (Days 4–6)

| ID | Agent | Task | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| P2-01 | A3 | Build FastAPI middleware wrapper around pais_intervention_score() | HIGH | 4 hrs |
| P2-02 | A3 | Implement Redis session store for UserProfile persistence | HIGH | 3 hrs |
| P2-03 | A3 | Implement circuit breaker state machine with 72h expiry | HIGH | 3 hrs |
| P2-04 | A3 | Build friction injection interface (SOFT/MEDIUM/HARD/PLATFORM_FLOOR responses) | HIGH | 4 hrs |
| P2-05 | A3 | Containerise with docker-compose (API + Redis + test harness) | MEDIUM | 2 hrs |
| P2-06 | A3 | Latency benchmark: p95 < 50ms end-to-end; optimise if needed | HIGH | 2 hrs |
| P2-07 | A3 | Integration test: full request → score → friction injection → response | HIGH | 2 hrs |

PHASE 3 — GOVERNANCE LAYER (Days 7–9)

| ID | Agent | Task | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| P3-01 | A4 | REST endpoint: GET/PUT /user/override-settings (30-day expiry enforced) | HIGH | 3 hrs |
| P3-02 | A4 | REST endpoint: GET/PUT /platform/floor-config (admin only) | HIGH | 2 hrs |
| P3-03 | A4 | Immutable audit log schema (PostgreSQL): every intervention decision logged | HIGH | 3 hrs |
| P3-04 | A4 | Third-party auditor read-only API endpoint | MEDIUM | 2 hrs |
| P3-05 | A4 | User override UX: ≤ 2 clicks to dismiss any non-PLATFORM_FLOOR intervention | HIGH | 3 hrs |
| P3-06 | A4 | Ratchet rule: 3 dismissals in 72h → circuit breaker notification (non-blocking) | HIGH | 2 hrs |
| P3-07 | A4 | Governance unit tests: override, expiry, audit log integrity | HIGH | 2 hrs |

PHASE 4 — VALIDATION & GO/NO-GO (Days 10–12)

| ID | Agent | Task | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| P4-01 | A5 | 5,000-trial Monte Carlo on integrated stack; compute final F1 and scaffolding_fp | CRITICAL | 3 hrs |
| P4-02 | A5 | Run all 12 archetype edge cases end-to-end through middleware | CRITICAL | 2 hrs |
| P4-03 | A5 | Latency regression test: confirm p95 < 50ms under load (100 concurrent users) | HIGH | 2 hrs |
| P4-04 | A5 | Governance audit: verify every intervention is logged; verify override works | HIGH | 2 hrs |
| P4-05 | A5 | Produce validation_report with PAIS_VIABLE: true/false + evidence | CRITICAL | 3 hrs |
| P4-06 | A5 | If PAIS_VIABLE = false: document exact kill condition and root cause | CRITICAL | 2 hrs |
| P4-07 | A5 | Assembly review: share validation_report with all 8 models for Round 4 | HIGH | 1 hr |

3  MILESTONES & CLEAR EXPECTATIONS

| M0 Day 1 EOD | ARS Recalibrated ✅ Success: T1 + T3 pass. Monte Carlo: atrophy_f1 ≥ 0.80, scaffolding_fp ≤ 0.10. | ❌ Failure / Halt: If F1 < 0.80 after recalibration: escalate to assembly. Do not proceed to Phase 1. |
| --- | --- | --- |

| M1 Day 3 EOD | Differential Diagnosis Hardened ✅ Success: 12 archetype tests pass. 0 ND false positives. Uncertain rate < 15%. | ❌ Failure / Halt: If ND false positives > 0: halt. Redesign classification prior before middleware. |
| --- | --- | --- |

| M2 Day 6 EOD | Middleware Integrated ✅ Success: End-to-end latency p95 < 50ms. All unit tests pass in container. | ❌ Failure / Halt: If latency > 50ms: profile and optimise before governance layer. |
| --- | --- | --- |

| M3 Day 9 EOD | Governance Layer Live ✅ Success: User override works in ≤ 2 clicks. Audit log immutable. 30-day expiry enforced. | ❌ Failure / Halt: If override UX requires > 2 clicks: redesign before validation. |
| --- | --- | --- |

| M4 Day 12 EOD | GO / NO-GO Decision ✅ Success: PAIS_VIABLE = true (F1 ≥ 0.80, scaffolding_fp ≤ 0.10, latency < 50ms, governance audit clean). | ❌ Failure / Halt: If PAIS_VIABLE = false: publish kill condition report. Do not deploy. Return to assembly. |
| --- | --- | --- |

4  FALSIFIABILITY CONTRACT

These are the only numbers that matter. The project lives or dies on them.

| Metric | Current (Run 1) | Required | Kill Condition |
| --- | --- | --- | --- |
| atrophy_f1 | 0.0 ❌ | ≥ 0.80 | < 0.80 after Phase 0 → halt |
| scaffolding_fp_rate | 0.0 ✅ | ≤ 0.10 | > 0.10 → differential diagnosis broken |
| ND false positives | N/A | = 0 | > 0 → do not deploy |
| API latency p95 | N/A | < 50ms | > 50ms → optimise before governance |
| Unit tests passing | 4/6 ❌ | 6/6 | < 6/6 after Phase 0 → halt |
| Override UX clicks | N/A | ≤ 2 | > 2 → redesign governance layer |

The assembly's convergence statement: run python pais_v1_scoring.py. If it exits 0 with atrophy_f1 ≥ 0.80 AND scaffolding_fp ≤ 0.10, PAIS is viable. If either assertion fails, the detection paradigm is broken and the assembly does not proceed to deployment architecture.

PAIS Implementation Plan  ·  Claude Sonnet 4.6  ·  Democratic Epistemic Infrastructure Assembly  ·  Round 3 Output